COLLECTION AND VERIFICATION OF MATERIAL SOCIAL DATA FOR PROJECT PLANNING FROM LONGUO WARD IN MOSHI MUNICIPALITY AND KELAMFUA MOKALA WARD AT ROMBO DISTRICTS

RESEARCH Ref. No. ACWF/RESEARCH/HO/2011/01

Contents

- Background

- The assignment

- Methodology

- Team Composition and Tasks

- Budget

# Background

ACWF (African Child Welfare Foundation Registered Trustees) is a development support NGO that works with, vulnerable and marginalized groups to overcome poverty and misery focusing on the plight of African children by improving Socio-Economic standards of living and promoting sustainable Earth Environment. Under its enacted constitution, the foundation prevails within the Tanzanian Laws and Regulations accordingly

We are recently (may 2011) registered under the trustee Incorporation act (Cap. 318 R.E. 2002) by the Administrator general of trustees and issued certificate No. 4170. ACWF has its offices in Moshi and Rombo Districts in Tanzania, Most activities are coordinated from Moshi. P.O. Box 1722 Arusha, greenkavishe@hotmail.com, text +255687060791, land line +255272753936. Website www.acwf.or.tz. We are currently establishing our physical structures, manpower (the bulk of which shall be a network of volunteers supported by a small permanent team of trustees and staff) and developing a strategic plan needing hence the need for this and other researches to come.

ACWF  is committed to change and transformation of lives through strategic partnerships with the poor. Among the first areas of operation for ACWF shall be Lunguo Ward in Moshi Municipality and Kelamfua Mokala ward in Rombo District. This assignment is therefore aimed to achieve a comprehensive collection verification and analysis of Data that shall lead to a working plan for ACWF in this area.

ACWF hereby requesting willing volunteers to carry this research as detailed below, volunteers may make themselves available for the assignment (see paragraph 5 below) or can provide the requisite funds and ACWF shall then procure volunteers with qualification through advertisement for expression of interest

RESEARCH: Ref: No. ACWF/RESEARCH/HO/2011/01 COLLECTION AND VERIFICATION OF MATERIAL SOCIAL DATA FOR PROJECT PLANNING FROM LONGUO WARD IN MOSHI MUNICIPALITY AND KELAMFUA MOKALA WARD AT ROMBO DISTRICTS

# 2.0	The Assignment

The Assignment is intended to cover the following core activities;

- Collect the Material Social Data (MSD) from the various sources including governmental and non governmental entities and other stake holders (see paragraph 3 Methodology below)

Basic Data to be collected

- Demographic Data, population, Age groups, Number of Old persons, Dis abled, HIV ADIS prevalence, school attendance, employment etc. etc.

- Data on Governmental and non governmental organisations operating at the ward and details and impact of their activities in the area and the impact they are making commensurate to ACWF goals, this shall be vital to focus ACW activities in the Working plan.

- Geographical and economic data on the area. Environment, recourses, and the like.

- Any other as proposed by the Research team or as encountered and found relevant during the research.

Data collected shall be analysed to produce a report that shall be a basis for the ACWF working plan.

- To verify the accuracy and completeness of MSD disclosures on all aspects as required by ACWF and other stake holders (the researchers or sponsors are free to extend this research to also suit their specific need).

- To analyze collected and verified data on two wards in order to make informed judgments about the social status in order to propose projects commensurate to ACWF objectives.

- To produce reports that are clearly intelligible to the non-specialist, highlighting any cause for concern the analyzed information reveals.

# 3.0	Methodology

The methodology is based on the scope of work envisaged for this assignment and shall be divided into three phases as follow:-

Phase 1:   Collection of information and Verification

- Sending questionnaire to different offices in the District , Ward and Village,

- Accessing Websites eg. National Census and other websites with requisite data.

- Accessing Reports eg. from libraries, government offices achives and other stake holders based in the research area. Or any other method suggested by Researches etc.

- Physical collection by site visits

- Verification of Data collected shall be up dated and calibrated and verified during field visits

- Draft report on phase one has to be produced and distributed to ACWF and other interested stake holders for review and comments before a Final Report is Drawn. ACWF may request elaboration or further collection and verification of Data upon which another Draft Report has to be compiled before commencement of Phase two.

Phase 2:   Analysis of the Material Project Information

This shall be to carry out detailed analysis of the information collected with a focus on documenting and quantifying extreme vulnerabilities and suggesting projects aimed at their containment

A draft report has to be produced and distributed to ACWF and other interested stake holders for review and comments before a Final Report is Drawn

The final Report shall remain a property of ACWF, Researchers, Sponsors and other stake holders. The Final Report may be published in ACWF website.

# 4.0	Research Team Composition and Tasks

4.1 	Team Composition

The Study Team shall be composed of the following;

- Lead Consultant			- 	Nshekanabo Wilbroad

- Research Team Consultants	-	Volunteers

- Support Staff 			-	Driver, Helpers etc. organized by ACWF.

  - Team Tasks

The tasks for the Research Team Members shall be as follows;

- Lead Consultant

- The Lead Consultant will be leading the assurance team and co-ordinate the whole assignment.

- He will mainly oversee the preparations of the Template for collecting the data and lead the overall analysis of the Material Social Data collected.

- He will lead preparation of the reports for submission to  ACWF and Copenhagen School of Social Work

- He will be the liaison person to the ACWF and Other stake holders

- He will as much as possible participate in all team activities

- Will ensure transparency and good governance of the team

- Shall prepare a detailed working schedule for the program

- Will maintain good will and cooperation with all parties concerned, Shall ensure the team works with independence

- Research Team Members

- Will study this proposal, comment on it and suggest improvements and come up with a working paper agreeable by both ACWF, and other stake holders.

- Will be responsible for collecting and verifying the Material Social Data obtained from various sources as indicated earlier.

- Will make field visits to collect information and verify information collected otherwise and get the insight of target communities to enable proper analysis and make informed recommendations..

- Will participate to prepare the Reports at each Phase.

- Will ensure transparence and good governance of the team

- Will ensure good will and cooperation for all parties concerned

- Shall work with independence.

# 5.0	Budget

- The estimated time for a comprehensive data collection is estimated to be a minimum of eight weeks. Researchers have to be based in ACWF Moshi office/Homestay, they will visit Rombo (about 60Km from Moshi) and stay for short durations necessary for field work in That area only. Researchers have to organize for their cost of stay as per ACWF rates (see our website). The contribution shall cover accommodation, meals, transport (connected to the assignment) , stationery and office

- Renumerations for the Lead Consultant (He is not a Voteer, He is a social worker outsourced by ACWF) is USD 1,000 for the entire assignment.

- The minimum team members is 2 persons and Maximum is 8 persons

- The total Budget is therefore the total cost of items 1 and 2 with respect to the actual team size and agreed duration

- The assignment shall be achieved after a total budget is concluded either as organized by volunteers actually doing the assignment or by a volunteer (s) donation and ACWF procurement of the Research team

# 6.0	More Information on Volunteers (Researchers Placement)

- Each Research team member and sponsor shall be awarded a "certificate of service” and a stamped and signed copy of the final report and shall be kept posted on the developments arising from the Report.

- Volunteers shall be placed in a hostel operated by ACWF at Moshi Lunguo B, shall be moved on to Rombo and be placed in Hostel run by ACWF. They will have to travel to Rombo only when they have to verify Data connected to Kelamfual Mokala ward which is in Rombo (60kma from Moshi).  All Data Collection analysis and compilation shall be done at ACWF office in Moshi.

- Volunteers shall be expected to follow the normal working hours prevalent in the government offices in Tanzania. That is five days a week, eight hours a day with one hour lunch break.  However the group is expected to have and stick to its own working plans

- ACWF is already active in the following activities which now  need to be properly planned in a professional and sustainable way. Researches shall have an opportunity to visit these projects during their stay with us

- Volunteer hosting and placement

- Student support projects

- ACWF Website forum

- Research Projects

Various Projects at the following schools

- Mairiva Secondary School in

- Kwangao Primary School in Rombo

- Kibo Secondary school in Moshi

- Volunteer shall move around using public transport, they are also expected to walk around the village during DATA verification. Both wards have an area manageable by walking , Hostels,  offices and places of work are all at a reasonable walking distance, Public transportation is cheap in the area, commuting with towns shall cost around Tshs 300 a trip, fare between Moshi and Rombo are around Tshs 3,000/=  one way.  Taxis within the town are around Tshs 3000  to 5000/= within the municipality. (1usd is roughly  Tshs 1500).

- After the research is done, Researchers may be willing to stay on for other activities including tourism to our game reserves, coast and Zanzibar, and eco tourism. While this activity is not part of the Research ACWF shall be handy to provide the requisite handling.

Elsewhere please find CV of the supervisor of the students Mr. Nshekanabo Wilbroad

If you are interested and wish further clarification or wish to take up this challenge kindly contact ACWF President through this e-mail address greenkavishe@hotmail.com

6.0 CURRICULUM VITAE NSHEKANABO WILBROAD

PERSONAL BIODATA

Full Name		:	Nshekanabo Wilbroad

Sex			:	Male

Marital status	:	Single

Date of Birth		:	4th June 1981

Mobile			:	+255714504381 and

E-mail			:	nshekanabo2009@yahoo.co.uk

EDUCATIONAL BACKGROUND

| 2010 - Now | University of Dar Es Salaam | Pursuing MA. Development studies |
| --- | --- | --- |
| 2008-2009 | Moshi University College of Cooperative and Business Studies (MUCCoBS) in Collaboration with Sokoine University of Agriculture | Post Graduate Diploma in Community Development |
| 2005-2008 | Community Development Training Institute (CDTI – Tengeru) | Advance Diploma in Community Development |
| 2001 - 2005 | Eckenforde High School in Tanga | Advanced Certificate of Secondary Education |
| 1997 -2000 | Kaigara Secondary School in Kagera | Certificate of Secondary Education |
| 1990 - 1996 | Rubungo Primary School in Kagera | Certificate of Primary Education |

OTHER COURSES

| 2005 | Itunda Driving School in Dar Es Salaam | Driving Certificate leading to qualify for Driving License class E |
| --- | --- | --- |
| 2007 | Yombo Technical College Dar Es Salaam | Computer course (Introduction to ICT, MS Word, MS Excel and SPSS |

EMPLOYMENT AND WORKING EXPERIENCE

| 2010 - Now | ACWF (African Child Welfare Foundation) and its sister organization AXIS (Axis of Good Foundation) | Consultant and Social worker |
| --- | --- | --- |
| 2008 - Now | Ministry of Community Development Gender and Children welfare | Community Development Officer (CDO) |
| 2009 – Now | Sustainable Community Development Initiative Association (SCODIA) | Project Facilitator |
| 2004 – 2008 | Tanzania Breweries Limited (TBL) Dar Es Salaam | Shift Supervisor |
| 2003 – 2004 | Seven Up Limited Dar Es Salaam | Shift Manager |

COMMUNITY ACTIVITIES ATTENDED

- Conducted Research on the Early Pregnancies among the primary School girls in Meru District

- Conducted Research on the Street Children in Moshi

PART TIME ACTIVITIES

- Consultant ACWF and AXIS Foundations dealing with extreme vulnerabilities in societies in Moshi and Rombo Districts

- Social Worker Tuna Haki Street Children Center in Moshi

- Facilitation of Workshops Related to Community Development

- Facilitation of Training towards SACCOS and Cooperative Management

- Assisting Communities in Projects identification and Management.

CERTIFICATES

- Post Graduate Diploma in Community Development conferred by Sokoine University of Agriculture

- Academic transcript by Moshi University College of Co-operative and Business Studies MUCCoBS

- Advance Diploma in Community Development (Management of community Development Programs) conferred by Community Development Training Institute (CDTI) -TENGERU

- Academic Performance Report: Advanced Diploma of Community Development Training Institute (CDTI) – TENGERU